## Overview
Glimmora Go — Spec Sheet
Frontend team: admin panel (Next.js) + Kirana PWA + public tracking
Generated from Glimmora_Go_SOW.docx + Frontend Tracker + current codebase
Status legend
Done | Built, tested, in production-ready state
Partial | Skeleton exists but core sub-features missing
TODO | Not yet built
N/A | Owned by another team (backend/app-dev/infra) or deferred
Sheets
Roles | All 8 roles, access surface, primary responsibilities
Permissions | Role × surface × read/write matrix
Admin Panel | Every page with its features + subfeatures + status
Kirana PWA | Every page with its features + subfeatures + status
APIs | All HTTP endpoints with auth requirements
Schema | Prisma models and what uses them
Gaps | Items from the SOW not yet built

## Roles
# | Role | Surface | Seeded login | Primary responsibilities | Scoping | Status
1 | Super Admin | Admin Panel (full) | admin@glimmora.ai / admin123 | Everything: cities, fares, coupons, drivers, rides, reports, admins, partners, referrals | Global (all cities) | Done
2 | Admin | Admin Panel (full except admin user mgmt) | admin2@glimmora.ai / admin123 | Same as Super Admin minus the ability to create/delete admin users | Global (all cities) | Done
3 | City Admin | Admin Panel (scoped) | rewa.admin@glimmora.ai / admin123 | Driver approvals, local fare, ride monitoring, reports, partner approvals — only for assigned city | One cityId from Admin.cityId | Done
4 | Verifier | Admin Panel (drivers + docs only) | verifier@glimmora.ai / admin123 | Approve/reject driver KYC documents. Sees only PENDING drivers. No access to other modules. | All cities, PENDING drivers only | Done
5 | Support / QA | Admin Panel (read + tickets write) | support@glimmora.ai / admin123 | Monitor live rides, riders, reports, SOS; triage and resolve support tickets | Read-only global; write on tickets | Done
6 | Viewer | Admin Panel (read-only) | viewer@glimmora.ai / admin123 | Observer across all modules. Cannot write. | Read-only global | Done
7 | Kirana Agent | Kirana PWA | phone + 6-digit OTP | Book rides on behalf of walk-in customers, view own bookings + commission, manage profile | Own shop only (partnerId) | Done
8 | Trusted Contact / Ride Recipient | Public Tracking Link | no login (opaque token URL) | View one ride's live status + map. Used by riders' 'share-my-ride' and trusted-contact auto-SMS. | One ride only via trackingToken | Done

## Permissions
Surface | Super Admin | Admin | City Admin | Verifier | Support | Viewer | Notes
Dashboard | W | W | R (own city) | — | R | R | Stats + recent rides
Rides | W | W | W (own city) | — | R | R | Cancel/complete/reassign/share
SOS Alerts | R | R | R (own city) | — | R | R | Live sidebar badge
Drivers list | W | W | W (own city) | R (PENDING only) | — | R
Driver docs | W | W | W (own city) | W | — | — | Per-document approve/reject + note
Riders | R | R | R | — | R | R | Search + lifetime spend
Fares | W | W | W (own city) | — | — | R | Per-city fare config
Concessions | W | W | — | — | — | R | Women/senior/children multipliers
Coupons | W | W | — | — | — | R | Flat/%, usage limit, expiry
Cities | W | W | — | — | — | R | Includes archetype defaults editor
Referrals | W | W | — | — | — | R | Auto-reward + manual override
Reports | R | R | R (own city) | — | R | R | Includes CSV export + city breakdown
Kirana Partners | W | W | W (own city) | — | — | R | Approve/reject + commission
Admins | W | — | — | — | — | — | Super Admin only
Tickets | W | W | W (own city) | — | W | R | SUPPORT role can triage
Audit / Compliance | R | R | — | — | — | R | Read-only log; fraud signals panel
Enterprise (B2B) | W | W | W (own city) | — | — | R | Corporate accounts + wallet
Track public | — | — | — | — | — | — | Public, opaque token
Kirana PWA | — | — | — | — | — | — | Separate auth; agents only

## Admin Panel
# | Page / Route | Feature | Sub-feature | Access (roles) | Status | Notes
AUTH
1 | /login | Admin login | Email + password, JWT session cookie, redirect to ?next= | public | Done
2 | /api/auth/logout (POST) | Logout | Clear session cookie | Authed | Done
DASHBOARD
3 | / | Dashboard stats | Rides today, revenue today, active drivers, SOS today | SUPER/ADMIN/CITY/SUPP/VIEW | Done | CITY sees own-city only
4 | / | Recent rides feed | Top 8 most recent rides with links | SUPER/ADMIN/CITY/SUPP/VIEW | Done
5 | / | DB-not-reachable banner | Friendly message when Prisma can't connect | all | Done
RIDES
6 | /rides | Ride monitoring table | 100-row list, rider + driver + city + fare + status + started | SUPER/ADMIN/CITY/SUPP/VIEW | Done
7 | /rides | Status filter pills | ALL / REQUESTED / MATCHED / IN_TRIP / COMPLETED / CANCELLED | all allowed | Done
8 | /rides | Live auto-refresh toggle | 15s polling, on/off, refresh counter | all allowed | Done | Socket.io replacement-ready
9 | /rides | Cancel ride | PATCH action=CANCEL; blocked on terminal | SUPER/ADMIN/CITY | Done
10 | /rides | Force-complete ride | PATCH action=COMPLETE; sets completedAt, fareFinal | SUPER/ADMIN/CITY | Done | Triggers referral reward
11 | /rides | Reassign driver | Inline select of APPROVED drivers in same city + PATCH | SUPER/ADMIN/CITY | Done
12 | /rides | Share public link | POST /api/rides/[id]/token → clipboard /track/[token] | SUPER/ADMIN/CITY | Done
SOS ALERTS
13 | /sos | SOS event log | Filtered to sosTriggered=true rides, LIVE pulse on active | SUPER/ADMIN/CITY/SUPP/VIEW | Done
14 | /sos | Stat cards | Active SOS, SOS today, all-time count | same | Done
15 | Sidebar | Live badge counter | Polls /api/sos every 30s; red pill when > 0 | same | Done
DRIVERS
16 | /drivers | Driver list | 100-row list with status/online/docs/rides count | SUPER/ADMIN/CITY/VERIF/VIEW | Done | VERIFIER sees PENDING only; CITY_ADMIN city-scoped
17 | /drivers | Status filter pills | ALL/PENDING/APPROVED/REJECTED/SUSPENDED | same | Done
18 | /drivers/[id] | Driver profile card | Status badge, city, phone, online, daily goal, rides, referral code | SUPER/ADMIN/CITY/VERIF | Done
19 | /drivers/[id] | Approve / Reject / Suspend / Pending | PATCH with optional verification note | SUPER/ADMIN/CITY | Done
20 | /drivers/[id] | Verification note banner | Shown when driver.verificationNote set | same | Done
21 | /drivers/[id] | Document list + per-doc review | Type, uploaded date, View file link, approve/reject + reviewNote | SUPER/ADMIN/CITY/VERIF | Done | VERIFIER can only write docs
— | /drivers/[id] | Document file upload UI | Pick type + file, POST /api/uploads/driver-doc, stored under public/uploads/drivers/ | SUPER/ADMIN/CITY/VERIF | Done
RIDERS
22 | /riders | Rider search + list | Phone/name search, language badge, ride count, lifetime spend, last ride, joined | SUPER/ADMIN/SUPP/VIEW | Done
— | API | Riders JSON API | GET /api/riders (q/limit/offset), GET /api/riders/[id] with rides + stats | riders:read | Done | For external clients and future rider app
FARES
23 | /fares | Per-city fare editor | Base fare, per km, per min, minimum fare | SUPER/ADMIN/CITY (write) · VIEW (read) | Done | CITY sees own city only
24 | /fares | Saved ✓ feedback | 2s confirmation after PUT | same | Done
CONCESSIONS
25 | /concessions | Per-city multipliers | Women, senior, children — default 0.85/0.80/0.90 | SUPER/ADMIN (write) · VIEW (read) | Done
COUPONS
26 | /coupons | Create coupon | Code, description, FLAT/PERCENT, amount, usage limit, expiry | SUPER/ADMIN | Done
27 | /coupons | List + usage stats | Used count / limit, expiry date, active/disabled/expired badge | same + VIEW read | Done
28 | /coupons | Disable / Enable / Delete | PATCH active flag / DELETE | SUPER/ADMIN | Done
CITIES
29 | /cities | Archetype defaults editor | Per-archetype (Metro/Small Town) defaults: radius, surge, payment options, base, perKm, perMin, minFare | SUPER/ADMIN (write) · VIEW (read) | Done | New cities inherit these
30 | /cities | Add city form | Name + state + archetype | SUPER/ADMIN | Done
31 | /cities | Per-city edit row | Archetype override, matching radius, surge, active toggle, payment pills | SUPER/ADMIN | Done
REFERRALS
32 | /referrals | Stat cards | Total / joined / rewarded with conversion % | SUPER/ADMIN (write) · VIEW (read) | Done
33 | /referrals | Top referrers list | Top 5 drivers by referredDrivers count | same | Done
34 | /referrals | Recent referrals table | Referee phone, rides done / 10, status (Pending/Joined/Rewarded), date | same | Done
35 | /referrals | Issue / Revoke reward | Manual toggle on Referral.rewardIssued | SUPER/ADMIN | Done
36 | /referrals | Mark joined | Manual toggle on refereeJoined | SUPER/ADMIN | Done
37 | /referrals | Recompute rewards button | Scans all drivers, grants rewards for any who crossed 10 rides | SUPER/ADMIN | Done
38 | automation | Auto-reward on ride complete | On PATCH action=COMPLETE, if driver was referred + hit 10 rides, extend referrer subscriptionUntil by 7 days | system | Done
REPORTS
39 | /reports | Range pills | Last 7 / 14 / 30 / 90 days | SUPER/ADMIN/CITY/SUPP/VIEW | Done
40 | /reports | Stat cards | Rides, revenue, completion %, active drivers | same | Done
41 | /reports | Charts | Rides-per-day bar, revenue line, booking-channel donut | same | Done | Chart.js
42 | /reports | By-city breakdown | Rides, completion %, revenue per city | same | Done
43 | /reports | Top drivers table | Top 10 by rides + revenue | same | Done
44 | /reports | CSV export | GET /api/reports/export?days=N → rides-Nd-YYYY-MM-DD.csv | same | Done | City-filtered for CITY_ADMIN
KIRANA PARTNERS (admin side)
45 | /partners | Partner list with status filter | Shop, owner, phone, city, commission %, bookings count, status + review note | SUPER/ADMIN/CITY (write) · VIEW (read) | Done
46 | /partners | Approve / Reject / Suspend | PATCH status + optional reviewNote | SUPER/ADMIN/CITY | Done
47 | /partners | Commission % editor | Per-partner override (default 10%) | same | Done
SUBSCRIPTIONS
— | /subscriptions | Subscription list + stats | All driver plans with active/expired/revoked status; active/total/revenue cards | SUPER/ADMIN (write) · VIEW (read) | Done
— | /subscriptions | Grant subscription | Pick approved driver + plan (DAILY/WEEKLY/MONTHLY) + amount; stacks on existing expiry | SUPER/ADMIN | Done
— | /subscriptions | Revoke / Reinstate | PATCH active flag; rolls back driver.subscriptionUntil if all plans inactive | SUPER/ADMIN | Done
TICKETS / COMPLAINTS
— | /tickets | Tickets list + counters | Open / In-progress / Total cards; status filter pills; city-scoped for CITY_ADMIN | SUPER/ADMIN/CITY/SUPPORT (write) · VIEW (read) | Done
— | /tickets | Create ticket | Subject, category, priority, description, optional rider/ride links | SUPER/ADMIN/CITY/SUPPORT | Done
— | /tickets/[id] | Ticket detail + triage | Status + priority + assignee + resolution note; linked rider/driver/ride | SUPER/ADMIN/CITY/SUPPORT | Done
AUDIT & COMPLIANCE
— | /audit | Audit event log | Filter by entity / admin / range (24h/7d/30d/90d); shows who + what + summary + IP | SUPER/ADMIN/VIEW (read) | Done | Hooked into drivers/coupons/partners/admins/subscriptions/tickets/corporates APIs
— | /audit | Fraud & compliance signals | Stale PENDING drivers, doc rejection repeats, unresolved SOS >24h, duplicate rider accounts, high-cancellation drivers | same | Done
— | /api/audit/export | CSV export | Download audit events over N-day range | same | Done
ENTERPRISE (CORPORATES)
— | /corporates | Corporate accounts list | Name, contact, city, members/rides count, wallet, status | SUPER/ADMIN/CITY (write) · VIEW (read) | Done
— | /corporates | Create corporate account | Name, GSTIN, contact (name/email/phone), city | SUPER/ADMIN/CITY | Done
— | /corporates/[id] | Corporate detail | Status + wallet + members + recent rides + wallet history | SUPER/ADMIN/CITY | Done
— | /corporates/[id] | Approve / Suspend / Review note | PATCH status + reviewNote | SUPER/ADMIN/CITY | Done
— | /corporates/[id] | Members management | Add rider by phone (auto-creates rider), set employee ID, remove | SUPER/ADMIN/CITY | Done
— | /corporates/[id] | Wallet top-up / debit | Manual ledger entries with note; affects walletBalance transactionally | SUPER/ADMIN/CITY | Done | Ride-fare deduction not wired yet — depends on payments
ADMIN USER MGMT
48 | /admins | Create admin form | Email, name, password (8+), role, city picker (if CITY_ADMIN) | Super Admin only | Done
49 | /admins | Admin list | Name, email, role badge, city, active/disabled, joined | Super Admin only to see controls | Done | Non-super sees list read-only
50 | /admins | Enable / Disable / Delete | Self-delete + self-deactivate blocked | Super Admin only | Done
CROSS-CUTTING
51 | sidebar | Role-filtered nav | Hide pages user can't access; role label under logo | all | Done
52 | layout | Session enforcement | requireAccess(surface) on every page; redirects unauthorized to / | all | Done
53 | API | requireWrite + cityMismatch | Centralized guards on every API mutation | all | Done
54 | global | i18n Hindi + English toggle | next-intl across all admin strings | all | TODO | Tracker #20, Low priority
55 | global | Audit log / compliance module | Track who changed what, when + fraud signals | SUPER/ADMIN | Done | Shipped in /audit + /api/audit
56 | global | Enterprise admin console | Corporate/fleet accounts with wallet + members | — | Done | Shipped in /corporates; ride-fare deduction waits on payments
57 | global | Socket.io realtime rides | Replace polling with live push | — | TODO | Backend dependency

## Kirana PWA
# | Page / Route | Feature | Sub-feature | Access | Status | Notes
PUBLIC (no session)
1 | /k/signup | Partner onboarding form | Shop name, owner name, 10-digit phone, city picker | public | Done
2 | /k/signup | Success screen | 'Application submitted' with link to /k/login | public | Done
3 | /k/login | Phone → OTP request | 10-digit validation, 'Send OTP' triggers /api/kirana/otp/request | public | Done
4 | /k/login | OTP entry screen | 6-digit code input, auto-surfaced in dev mode, back button | public | Done
5 | /k/login | Verify + session | /api/kirana/otp/verify sets glimmora_kirana_session cookie | public | Done
AUTHED (any status)
6 | /k (any) | Pending / Rejected / Suspended gate | Blocks app with status-specific message + admin's review note + sign-out button | Kirana partner (non-APPROVED) | Done
7 | /k (logout) | Sign out | POST /api/kirana/logout clears cookie → redirect /k/login | Kirana partner | Done
APPROVED PARTNER
8 | /k | Dashboard today stats | Today's bookings count, today's commission | Approved partner | Done
9 | /k | Lifetime commission card | Total earned on COMPLETED rides × commissionPct | same | Done
10 | /k | CTA button | 'Book a ride for a customer' → /k/book | same | Done
11 | /k | Recent 5 bookings | Pickup → drop, status badge, date, fare | same | Done
12 | /k/book | Customer section | Rider phone (10-digit), optional name | Approved partner | Done
13 | /k/book | Pickup section | Address + lat + lng | same | Done
— | /k/book | Map-based pickup/drop picker | Leaflet + OSM Nominatim; click map or search address to set pickup and drop | same | Done
14 | /k/book | Drop section | Address + lat + lng | same | Done
15 | /k/book | Concession selector | None / Women / Senior / Children — applied to fare | same | Done
16 | /k/book | Fare estimate | PUT /api/kirana/bookings returns fare + distance + duration + your commission | same | Done
17 | /k/book | Confirm → create ride | POST /api/kirana/bookings creates Ride with bookingChannel=KIRANA, bookedByPartnerId=self | same | Done
— | /k/book | SMS notification to rider | Text rider their pickup code + ETA | same | TODO | Needs MSG91
— | /k/book | Auto-match driver | Find nearest APPROVED online driver and assign | same | TODO | No matching engine yet
18 | /k/bookings | Bookings history list | All partner's rides, status, rider phone, fare, commission earned | Approved partner | Done
19 | /k/bookings | Commission per row | Shown only when ride is COMPLETED | same | Done
20 | /k/profile | Profile read-only | Shop, owner, phone, city, commission %, joined, status badge | Approved partner | Done
21 | /k/profile | Sign out button | Same as dashboard logout | same | Done
— | /k/profile | KYC document upload + status | Pick type + file, upload to /api/kirana/documents; shows per-doc PENDING/APPROVED/REJECTED badge | same | Done
NAVIGATION + LAYOUT
22 | layout | Mobile-first shell | Top header with shop name, bottom nav (Home/Book/History/Profile) | Approved partner | Done
23 | layout | Session guard | requireKirana() on every protected page | all kirana routes | Done
PWA SHELL
— | manifest | Web App Manifest | public/manifest.webmanifest scoped to /k/ with name/icons/theme/start_url | public | Done
— | icons | App icons + apple-touch | 192/512 PNG + maskable 512 + 180 apple-touch, brand orange 'GG' monogram | public | Done | Generated via scripts/build-pwa-icons.py
— | service-worker | Service worker (/sw.js, scope /k/) | Cache-first static, network-first kirana APIs, offline fallback to /offline.html | public | Done | Service-Worker-Allowed header set in next.config.js
— | install | Install prompt component | Captures beforeinstallprompt, shows 'Add to home screen' banner with dismiss persistence | Approved partner | Done
— | push | Push notifications | Driver matched / arrived / completed alerts | system | TODO | SW ready; needs VAPID + backend trigger
CROSS-CUTTING
24 | OTP | 6-digit, 5-min TTL | OtpRequest table; single-use (usedAt timestamp) | system | Done
25 | OTP | MSG91 send | Actually send the code via SMS | system | TODO | Stubbed; returns devCode in dev
26 | fare | Haversine + concession | src/lib/fare.ts shared with future rider/driver apps | system | Done
27 | commission | Payout / settlement | Actually paying partners their earned commission | system | TODO | Tracks earned; no payout flow
29 | i18n | Hindi + English toggle | react-i18next across all kirana strings | system | TODO | Low priority

## APIs
Method | Path | Purpose | Auth / permission | Status
POST | /api/auth/login | Admin email+password login, sets session cookie | public | Done
POST | /api/auth/logout | Clear admin session | authed | Done
POST | /api/cities | Create city (uses archetype defaults) | cities:write | Done
PATCH | /api/cities/[id] | Update archetype/radius/surge/active/payments | cities:write | Done
PUT | /api/cities/[id]/fare | Update fare config | fares:write + city scope | Done
PUT | /api/cities/[id]/concessions | Update concession multipliers | concessions:write | Done
PUT | /api/archetypes/[archetype] | Edit Metro/Small Town defaults | cities:write | Done
PATCH | /api/drivers/[id] | Approve/reject/suspend driver + note | drivers:write + city scope | Done
GET | /api/drivers/[id]/documents/[docId] | Fetch single driver document | documents:read + city scope | Done
PATCH | /api/drivers/[id]/documents/[docId] | Approve/reject driver doc + review note | documents:write + city scope | Done
DELETE | /api/drivers/[id]/documents/[docId] | Delete driver doc + file | documents:write + city scope | Done
POST | /api/uploads/driver-doc | Upload driver doc file to storage | documents:write + city scope | Done
GET | /api/riders | List riders (q/limit/offset) | riders:read | Done
GET | /api/riders/[id] | Rider detail with recent rides + stats | riders:read | Done
GET | /api/subscriptions | List subscriptions (optional driverId/active filters) | subscriptions:read | Done
POST | /api/subscriptions | Grant subscription (stacks on existing expiry) | subscriptions:write | Done
PATCH | /api/subscriptions/[id] | Revoke / reinstate subscription | subscriptions:write | Done
GET | /api/tickets | List tickets (status/category/q filters, city-scoped) | tickets:read | Done
POST | /api/tickets | Create ticket | tickets:write | Done
PATCH | /api/tickets/[id] | Update status/priority/assignee/resolution | tickets:write + city scope | Done
GET | /api/audit | List audit events (entityType/admin/since filters) | audit:read | Done
GET | /api/audit/export | CSV export of audit events | audit:read | Done
GET | /api/corporates | List corporates (status filter, city-scoped) | corporates:read | Done
POST | /api/corporates | Create corporate account | corporates:write | Done
PATCH | /api/corporates/[id] | Update status / review note / contact | corporates:write + city scope | Done
POST | /api/corporates/[id]/members | Add rider to corporate (auto-creates rider) | corporates:write | Done
DELETE | /api/corporates/[id]/members/[memberId] | Remove member | corporates:write | Done
POST | /api/corporates/[id]/top-up | Credit / debit corporate wallet (transactional) | corporates:write | Done
PATCH | /api/rides/[id] | Cancel / Complete / Reassign driver | rides:write + city scope | Done
POST | /api/rides/[id]/token | Generate or fetch public tracking token | rides:write + city scope | Done
POST | /api/coupons | Create coupon | coupons:write | Done
PATCH | /api/coupons/[id] | Toggle active | coupons:write | Done
DELETE | /api/coupons/[id] | Delete coupon | coupons:write | Done
PATCH | /api/referrals/[id] | Manual reward issue/revoke | referrals:write | Done
POST | /api/referrals/recompute | Recompute all pending referral rewards | referrals:write | Done
GET | /api/reports/export | CSV download, city-filtered | reports:read | Done
GET | /api/sos | Active SOS count (sidebar badge) | sos:read + city filter | Done
POST | /api/admins | Create admin user | SUPER_ADMIN | Done
PATCH | /api/admins/[id] | Enable/disable, change role/city/password | SUPER_ADMIN | Done
DELETE | /api/admins/[id] | Delete admin | SUPER_ADMIN | Done
PATCH | /api/partners/[id] | Approve/reject/suspend + commission % | partners:write + city scope | Done
GET | /api/track/[token] | Public ride state for tracking page | public | Done
POST | /api/kirana/signup | Partner application (creates PENDING) | public | Done
POST | /api/kirana/otp/request | Generate 6-digit OTP (phone must belong to a partner) | public | Done
POST | /api/kirana/otp/verify | Verify OTP + set kirana session cookie | public | Done
POST | /api/kirana/logout | Clear kirana session | kirana session | Done
PUT | /api/kirana/bookings | Fare estimate without creating | kirana session (any status) | Done
POST | /api/kirana/bookings | Create booking (REQUESTED ride with bookedByPartnerId) | kirana session (APPROVED only) | Done

## Schema
Model / Enum | Purpose | Key fields | Used by | Status
Admin | Admin panel users | email, name, passwordHash, role, cityId | Login, /admins page | Done
AdminRole (enum) | 6 roles | SUPER_ADMIN, ADMIN, CITY_ADMIN, VERIFIER, SUPPORT, VIEWER | RBAC matrix | Done
Rider | Ride customers | phone (unique), name, language | /riders, kirana signup auto-creates | Done
Driver | Fleet drivers | phone, name, cityId, status, online, lat/lng, referredById, referralRewardGranted | /drivers | Done
DriverStatus (enum) | Driver KYC states | PENDING, APPROVED, REJECTED, SUSPENDED | driver detail | Done
DriverDocument | KYC docs per driver | driverId, type, fileUrl, status, reviewNote | driver detail + upload UI | Done
DocumentType (enum) | Doc categories | LICENSE, RC, INSURANCE, AADHAAR, PAN | driver docs | Done
DocumentStatus (enum) | Doc review states | PENDING, APPROVED, REJECTED | driver docs | Done
City | Cities served | name, state, archetype, matchingRadiusKm, surgeMultiplier, paymentOptions, active | /cities, fare/concession, partner/driver scoping | Done
CityArchetype (enum) | Tier | METRO, SMALL_TOWN | Drives defaults + UI | Done
ArchetypeDefaults | Tier defaults | archetype (PK), radius, surge, payments, baseFare, perKm, perMin, minFare | /cities archetype editor, applied on new-city create | Done
FareConfig | Per-city fare rules | cityId (unique), baseFare, perKm, perMin, minimumFare, women/senior/children multipliers | /fares, /concessions | Done
Ride | Trips | riderId, driverId, cityId, pickup/drop, fareEstimate, fareFinal, status, bookingChannel, trackingToken, bookedByPartnerId, sosTriggered | /rides, /track, /sos, /reports, kirana bookings | Done
RideStatus (enum) | Lifecycle | REQUESTED, MATCHED, EN_ROUTE, ARRIVED, IN_TRIP, COMPLETED, CANCELLED | Everywhere | Done
BookingChannel | Where a ride came from | APP, SMS, WHATSAPP, KIRANA, IVR | Reports, kirana rides | Done
ConcessionType | Fare discount category | NONE, WOMEN, SENIOR, CHILDREN | Fare calc | Done
Coupon | Promo codes | code (unique), discountType, amount, usageLimit, usedCount, validUntil, active | /coupons | Done
DiscountType | Coupon type | FLAT, PERCENT | coupons | Done
Referral | Driver-to-driver referrals | referrerDriverId, referrerRiderId, refereePhone, refereeJoined, ridesCompleted, rewardIssued | /referrals manual controls | Done
Subscription | Driver sachet packs | driverId, plan, amount, startedAt, expiresAt, active | /subscriptions admin + referral reward extends this | Done (admin grant; no driver-side purchase UI)
SubscriptionPlan | Sachet durations | DAILY, WEEKLY, MONTHLY |  | Done
KiranaPartner | Agent/kirana partners | phone (unique), shopName, ownerName, cityId, commissionPct, status, reviewNote | /partners, Kirana PWA | Done
PartnerStatus | Partner KYC states | PENDING, APPROVED, REJECTED, SUSPENDED | /partners | Done
PartnerDocument | Partner KYC docs | partnerId, type, fileUrl, status | Kirana /k/profile upload + /partners/[id] review | Done
OtpRequest | Phone OTP codes | phone, code, purpose, expiresAt, usedAt | Kirana OTP flow | Done
OtpPurpose | OTP use cases | KIRANA_LOGIN, RIDER_LOGIN, DRIVER_LOGIN | Kirana now; rider/driver later | Done (only Kirana used)
Ticket | Complaints / support tickets | category, priority, status, assignee, rider/driver/ride/city links, resolution | /tickets + /tickets/[id] + audit hook | Done
TicketCategory | Ticket category | RIDE_ISSUE, SAFETY, PAYMENT, DRIVER_BEHAVIOR, APP, OTHER | ticket create form | Done
TicketStatus | Ticket lifecycle | OPEN, IN_PROGRESS, RESOLVED, CLOSED | /tickets pills | Done
TicketPriority | Ticket priority | LOW, NORMAL, HIGH, URGENT | /tickets priority badges | Done
AuditEvent | Admin action log | adminId/email/role, action, entityType, entityId, summary, changes (Json), ip, userAgent, createdAt | /audit + CSV export | Done
Corporate | Enterprise/fleet accounts | name, gstin, contact, cityId, walletBalance, status, reviewNote | /corporates | Done
CorporateStatus | Corporate KYC | PENDING, APPROVED, SUSPENDED | /corporates | Done
CorporateMember | Rider ↔ corporate mapping | corporateId, riderId (unique pair), employeeId, active | /corporates/[id] members tab | Done
CorporateTopUp | Wallet ledger entries | corporateId, amount (+/-), note, createdByAdminId, createdAt | /corporates/[id] wallet history | Done

## Gaps
# | Gap | Module | Owner per SOW | Blocks | Priority | Notes
1 | Rider React Native / PWA app | Rider | App Dev team | Every rider-side feature | P0 | SOW says RN; pragmatic swap to PWA
2 | Driver React Native / PWA app | Driver | App Dev team | Driver accept/location/earnings/docs | P0
3 | Matching engine (nearest online driver) | Backend | Backend team | Auto-assignment on ride create | P0 | src/lib/fare.ts has Haversine; add /api/rides/match
4 | MSG91 SMS gateway | Integrations | Backend team | OTP SMS, fare estimate, job push, receipts, safety | P0
5 | WhatsApp Business API (Gupshup/Wati) | Integrations | Backend team | WhatsApp lite booking bot, status, receipts | P1
6 | Scheduled ride matcher | Backend | Backend team | Pre-booked rides auto-match at T-15min | P1 | Vercel Cron can do this
7 | Offline driver SQLite + SMS job accept | Backend+RN | Backend + App Dev | Patchy-2G driver workflow | P1 | Big effort; RN only
8 | Panic phrase voice detection | RN | App Dev | Silent SOS | P2 | RN Voice + on-device keyword listener
9 | Trusted-contact SMS on ride start | Backend | Backend team | Auto-alert to emergency contact | P1
10 | Socket.io live tracking server | Backend | Backend team | Real-time position updates in /rides + /track | P2 | Currently polling
11 | Payment (Razorpay) | Integrations | Backend team | UPI/card fares, driver subscriptions | P1 | SOW says cash-only for MVP; fast-follow
12 | Driver subscription purchase flow | Driver PWA | App Dev + Backend | Actually charging drivers | P1 | Schema exists
13 | Driver referral share UI | Driver PWA | App Dev | Drivers referring drivers in-app | P1 | Backend reward logic is done
14 | Driver daily earnings goal screen | Driver PWA | App Dev | Progress bar + celebration | P2
15 | Driver demand heat map | Driver PWA | App Dev | Show clustering of rides to drivers | P2
16 | Rider share-my-ride button | Rider PWA | App Dev | User-facing trigger for /track/:token | P1 | Token API + page already exist
17 | Push notifications | RN/Backend | App Dev + Backend | Ride updates, promos | P2
18 | KYC document upload UI (drivers + partners) | Admin + PWA | Frontend + Backend | Actually getting documents uploaded | Done | Shipped — stored under public/uploads/ in dev; production should swap to Vercel Blob / S3
19 | i18n Hindi + English | All frontends | Frontend + App Dev | Vernacular UX | P3 | Low priority per tracker
20 | Complaints / tickets module | Admin | Frontend | Support role has nothing to operate on | Done | Shipped — /tickets + /tickets/[id] with triage, priority, assignment, resolution
21 | Audit log | Admin | Frontend + Backend | Compliance, who-changed-what | Done | Shipped — /audit with filters + CSV export + fraud signals; hooked into 9 mutating APIs
22 | Enterprise / corporate admin console | Admin | Frontend | B2B customer fleets | Done | Shipped — /corporates with members + wallet ledger; ride-fare deduction waits on payments
23 | Commission payout flow | Admin + PWA | Backend + Frontend | Actually paying partners | P2 | Earnings tracked; no payout
24 | Map-based pickup/drop picker (Kirana) | Kirana PWA | Frontend | Stop asking agents for lat/lng | Done | Shipped — Leaflet + Nominatim
25 | IVR / missed-call booking | Integrations | Backend | Non-smartphone rider channel | P3 | SOW explicitly deferred to Phase 2
26 | Driver subscription purchase UI | Driver PWA | App Dev + Backend | Drivers buying their own plan; admin grant exists | P1 | Admin /subscriptions shipped; waits on payments + Driver app
27 | VAPID push notifications | RN/PWA + Backend | App Dev + Backend | Booking status push to kirana partners | P2 | PWA service worker ready; needs backend trigger + VAPID keys
28 | Bookings detail + live track in Kirana PWA | Kirana PWA | Frontend | Partner can't watch a ride they booked | P1 | Token API + public /track page already exist
29 | Per-document DELETE in partner docs review | Admin | Frontend | Admins can approve/reject but not remove partner docs | P3